Document ref.

SAI
IDENTIFICATION

Recommendations Tracking Report

test2 audit
test2
Number of recommendations made: 7
Ratings
Priority	Risk areas identified
Urgent 3 / Regular 4	Governance 4 / Operational 1 / Reputational 1 / Financial 1 / Compliance 0 / Misappropriation of assets 0
Recommendations by type of entity	Importance of recommendations
State 5 / Region 0 / Municipality 1 / Activity Area 0 / Entity 1	Strategic 5 / Important, but not essential 2
Status	Repeated?
Implemented 1 / Started Implementation 1 / Partially implemented 2 / Final Stage Implementation 0 / Not started Implementation 3 / Not addressed 0 / No longer applicable 0	Total 7 / New 6 / Repeated 0 / Partially rep. 1

Progress of recommendations
Recommendation	Priority	Risk	Timeline	Current Status
Ensure that upon receipt of this report, the Action Plan for implementing the recommendations has been prepared by the Government and the same has been reviewed by the COPF. The Assembly of Kosovo should also ensure that the plan incorporates all recommendations given and accurately set out the actions, time limits and persons responsible for implementing the recommendations and monitoring them	Urgent	Governance / (State)	Upon receipt of KNAO Anual Audit Report	Implemented
The mail system should be updated to decrease downtime periods for the service	Regular	Operational / (Entity)	march of 2020	Not started Implementation
At least twice a year, the Assembly should review the progress made on the recommendations given, strengthen accountability measures and propose measures to eliminate all obstacles that may affect the non-implementation of recommendations.	Urgent	Governance / (State)	Upon receipt of the KNAO Anual Audit report,	Not started Implementation
Review the existing legal framework for improving air quality and propose legal initiatives for the functionalising the monitoring network and air pollution prevention measures;	Regular	Governance / (State)	Beginning of 2019	Partially implemented
Based on the Treasury quarterly reports, the Ministry of Finance should address all the challenges identified by line Ministries in implementing projects financed from borrowing. At any time and in all cases where it is considered necessary, the Government should be advised the appropriate measures to overcome the difficulties;	Regular	Financial / (State)	Fall of 2019	Partially implemented
Mayors should regularly discuss the reports of managers responsible for the implementation of action plans, and report to the Municipal Assembly at least twice a year on progress and challenges in this area.	Regular	Reputational / (Municipality)	Across 2018/2019	Started Implementation
The unemployment rate in the country is alarming; therefore, policies at the government and sectoral level should serve as a response to the unemployment situation created in the country. This can be achieved through adequate planning of the necessary human resources and financial capacities for policy implementation as well as through the establishment of sustainable monitoring mechanisms. Employment-related strategic priorities and sectoral employment objectives have not been properly monitored as monitoring is not based on sound analysis. The implementation of proactive labour market measures, especially during 2017, was impeded by major delays in the functioning of the Employment Agency, the lack of specialising of a number of unemployed people, the preparation of lists with a limited number of unemployed people to undergo the process of selection, and lack of prioritisation of long-term unemployed people during the selection process. These shortcomings make it impossible to identify the unemployed persons who are more likely to become long-term unemployed persons; do not provide equal opportunities for a significant number of unemployed persons, and affect the increase in the number of long-term unemployed persons.	Urgent	Governance / (State)	During the mandate	Not started Implementation